## How to complete
This excel sheet should be read together with the guidance notes which give more detailed information and practical examples. Note that cells with data in green contain formulas and should not be changed as they automatically calculate a total based on data entered in other cells (yellow cells).
0 Tab study parameters - Cells in yellow should be completed to the specifications of your trial - These data are the linked to formulas in the other tabs. Do not remove or add lines in this tab
0 Tab budget parameters - This tab contains the costs for the personnel involved in the trial. - These values should not be changed.
0 Tab Sponsor Cost - This tab needs to be completed with the estimated budget for the whole trial. For some of the activities, a fixed amount is proposed based on the above mentioned rates and real time estimations. In other cases cells needs to be completed if no link to the study parameters tab exists - carefully check formulas and guidelines - In the case of a fixed amount (FX) the margin is already included.
0 Tab Site costs BE / Site Costs NL - This tab is to be completed with the estimated budget per study visit for the participating sites (which should be consistent with the table of trial visits and procedures in the protocol) - The current lay-out is generic and should be made study specific
Copyright © 2018 by KCE Trials. All rights reserved. The budget tool and guidelines are developed by KCE Trials. If you wish to use this budget tool outside the KCE Trials Programme or the BeNeFit call, you should contact trials@kce.fgov.be. Tell us how and why you wish to use the tool. Please include your contact details: name, institution/company, address, telephone number, and email.

## Study Parameters
Trial | Number |  | DD/MM/YYYY
Note that the information in this sheet should reflect the most recent version of the protocol - in case of discrepancies, the protocol will prevail
Study Parameters
Study Title
Reference | Number |  | (assigned when selected)
Protocol version
Budget version date | DD/MM/YYYY
Number of subjects | Number of subjects screened BE
Number of subjects screened NL
Number of subjects randomised BE
Number of subjects randomised NL
Number of subjects completing BE
Number of subjects completing NL
| Total number of subjects randomised | 0
Number of visits per subject
Number of sites in BE
Number of sites in NL
Total number of sites |  | 0
Actual Date
Study timelines | FPI (First Patient In)
LPI (Last Patient In)
LPLV (Last Patient Last Visit)
DBL (Data Base Lock)
CSR (Clinical Study Report)
| Total duration of the project FPI to CSR (in months): |  | 0
| Total duration of the project where monitoring is needed FPI to DBL (in months): |  | 0
| Total duration of the project (in years) |  | 0
| Recruitment period (in months) |  | 0
Monitoring | Planned number of on-site monitoring visits per site (for the total duration of the study) this does not include initiation and close out visits
Planned number of remote monitoring contacts per site (for the total duration of the study)
Number of CRAs (min 2)
| Planned number of monitoring visits abroad |  | 0 | depending on the sponsor country this will be number of sites in BE or NL and will also depend on decision of outourcing monitoring to a coordinating centre in the other country (use C23 in case sponsor is in BE)
Expected number of reportable SAEs
cells in yellow are to be completed
Note on D1: will be completed automatically

## Budget Parameters
Trial |  | Number |  | DD/MM/YYYY
Budget Parameters
Study team involved
Position | Hourly rate
PM | 50 | Project Manager
CRA | 50 | Clinical Research Associate
CI | 100 | Chief Investigator
Co CI | 80 | Co-Chief Investigator
CTA | 35 | Clinical Trial Administrator
Auditor | 55 | Auditor
STAT | 60 | Statistician
DM | 50 | Data Manager
SN | 40 | Study Nurse
HE | 60 | Health Economist
PI | 100 | Principal Investigator
Pharm | 60 | Pharmacist
PI nonMD | 80 | Principal Investigator non MD
Add other roles if relevant
Other budget relevant info
Margin (in %) if applicable: |  | 10%
Overhead (in %) if applicable: |  | NA
VAT (in %) if applicable BE |  | 21%
VAT (in %) if applicable NL |  | 21%
START UP | 1000 | per site | this is an example for medium complexity study in a hospital setting to be adapted according to training requirement, team involved (eg. 200€ for GP)
Travel cost for monitoring (including any overnight stay - max 300€/visit) |  | 300
Travel cost per km | 0.346

## Sponsor Cost
|  | Units | No. of units | Team member | Unit cost | Cost (EURO) | Margin incl | Comments, typical values as guidance
Trial |  | Number | [5 empty] | DD/MM/YYYY
1 | Project Design and Set up
1a | • Clinical Study Protocol incl stats, economic input, any rework, meetings • Subject Information and Consent including translations • Budget calculation • KCE-ZonMw contract negotiation • Amendments |  |  | FX | 40000 | 40000 | 40000
1b | Country specific adaptations and translations |  |  | FX | 2000 | 2000 | 2000
1c | Site selection including feasibility assessment/visit |  | 0 | FX | 1000 | 0 | 0 | 1000€/site
1d | Collaborator/site contracts (set-up, negotiation and finalisation) |  | 0 | FX | 1000 | 0 | 0 | 1000€/collaborator/site - 200€/site if GPs
| Total Feasibility and contracts |  |  |  |  | 0 | 0
SUM | Project Design and Set up |  |  |  |  | 42000 | 42000
2 | Regulatory and Ethics Review
2a | Initial Leading Ethics Committee submission BE |  | 0 | FX | 2000 | 0 | 0 | 2000€ for initial submission
2b | Initial Leading Ethics Committee submission NL |  | 0 | FX | 2000 | 0 | 0 | 2000€ for initial submission
2c | Initial Ethics Committee submission in participating sites BE |  | 0 | FX | 500 | 0 | 0 | 500€ per site
2d | Initial Ethics Committee submission in participating sites NL |  | 0 | FX | 500 | 0 | 0 | 500€ per site
2e | Initial Documentation for the Regulatory Authorities BE |  | 0 | FX | 2000 | 0 | 0 | 2000€ for initial submission
2f | Initial Documentation for the Regulatory Authorities NL |  | 0 | FX | 2000 | 0 | 0 | 2000€ for initial submission
2g | Communication with EC during the Project |  | 0 | FX | 2000 | 0 | 0 | 2000€ per year
2h | Communication with Authorities during the Project |  | 0 | FX | 2000 | 0 | 0 | 2000€ per year (if applicable)
2i | Subject Insurance BE |  |  |  |  | 0 | 0
2i | Subject Insurance NL |  |  |  |  | 0 | 0
2j | Fees for EC and Authority submission if applicable | [6 empty] | indicate the fees that are charged by CMO for evaluation of protocols (NA in Belgium for academic trials)
SUM | [5 empty] | 0 | 0
3 | Monitoring
3a | Development of Monitoring Plan |  |  | FX | 1600 | 1600 | 1600
3b | Study Training - CRAs | hours | 0 | CRA | 50 | 0 | 0 | up to 16h per CRA
3c | Study Initiation Visit | hours | 0 | CRA | 50 | 0 | 0 | up to 16h per site
3d | Study Monitoring Visits | hours | 0 | CRA | 50 | 0 | 0 | typically 12h to 16h per visit all-in, depending on complexity
3e | Closure Visit | hours | 0 | CRA | 50 | 0 | 0 | up to 16h per CRA, per site
3f | Off-site monitoring and site contacts | hours | 0 | CRA | 50 | 0 | 0 | e.g. 4h per contact per site - but will depend on risk assessment, number of patients, number if data points - to be adapted in formula depending on study can be performed by data manager or CRA
3g | travel costs monitoring visits abroad | hours | 0 | FX | 300 | 0 | 0 | fixed cost for travel to sites or meetings
SUM | [5 empty] | 1600 | 1600
4 | Quality Assurance
|  |  |  | FX | 6000 | 6000 | 6000
SUM |  |  |  |  | 6000 | 6000 | 6000 | includes 2 days sponsor site, 2 days investigator site, preparation, reporting and follow-up
5 | TMF Handling & Administration
5a | TMF Preparation at start |  |  | FX | 1000 | 1000 | 1000
5b | Investigator Study File at start | hours | 0 | CTA | 35 | 0 | 0 | typically 4h per file
5c | Shipment and Distribution Services | hours |  | CTA | 35 | 0 | 0 | only occasionally applicable
5d | Administration and Documentation during trial | hours | 0 | CTA | 35 | 0 | 0 | up to 12h per site per year
5e | Site payment calculation | hours | 0 | CRA | 50 | 0 | 0 | 1h per site per payment, assuming 2 payments/yr
5e | Site payment calculation | hours | 0 | DM | 50 | 0 | 0 | 1h per site per payment, assuming 2 payments/yr
5e | Site payment calculation | hours | 0 | PM | 50 | 0 | 0 | 1h per site per payment, assuming 2 payments/yr
5f | Administration of Site Payments | hours | 0 | CTA | 35 | 0 | 0 | 1h per site per payment, assuming 2 payments/yr
5g | Archiving | fixed | 0 | NA | 250 | 0 | 0 | typically €250 per large box, assuming 2 sites in 1 box and 25 yrs archiving including general master file documents
SUM | [5 empty] | 1000 | 1000
6 | Safety
6a | Follow-up of and reporting of reportable Serious Adverse Events |  | 0 | FX | 200 | 0 | 0 | based on 4h per SAE all-in
6b | Safety Database set-up and use |  |  | FX | 10000 | 0 | 0
6c | DSMB Meetings & FU (if needed) |  | 0 | FX | 2000 | 0 | 0 | assuming 2 per year
6c | DSMB Meetings & FU preparation (if needed) | hours | 0 | STAT | 1000 | 0 | 0 | assuming 2 per year
6d | SAE Reconciliation | hours |  | DM | 50 | 0 | 0 | up to 16h
SUM | [5 empty] | 0 | 0
7 | Data Management
7a | • Design of eCRF • Design of Clinical Trial Database • Data Management Plan |  |  | FX | 75000 | 75000 | 75000 | € 75.000,00 for low complexity pragmatic trial € 125.000 for moderate complexity pragmatic trial
7b | • Data Coding AEs • Data Coding Medication • Data validation & QC • Importation of data ( ECG, lab, etc.) • Programming of queries • Running query software, cleaning and distributing queries • Query Resolution • Database lock |  | 0 | FX | 100 | 0 | 0 | € 100,00 per patient, for low complexity pragmatic trial € 200,00 per patient, for moderate complexity pragmatic trial
SUM | [5 empty] | 75000 | 75000
8 | Statistics, report and publication
8a | Statistical analysis plan, randomisation and statistical programming |  |  | FX | 10000 | 10000 | 10000
8b | • Generation of tables and listings • Statistical analysis and report • Clinical Study Report • Any subsequent analysis and report |  |  | FX | 40000 | 40000 | 40000
8c | Publication, incl revision |  |  | FX | 10000 | 10000 | 10000
SUM | [5 empty] | 60000 | 60000
9 | Project Management
9a | Project Management (not included in the above headings) BE | hours | 0 | PM | 50 | 0 | 0 | e.g. 0,5 FTE (=800h) per year. This is just an indication and needs to be adapted according to number of sites and complexity, extent of monitoring, ...
9b | Liaison KCE-ZonMw and Project Status Reports | hours | 0 | PM | 50 | 0 | 0 | up to 2h every 2 weeks at study start and during active recruitment period
9b | Liaison KCE-ZonMw and Project Status Reports | hours | 0 | PM | 50 | 0 | 0 | up to 2h every 4 weeks during follow-up period (after recruitment)
9c | Investigator Meeting(s), initial meeting includes time from PM, CI, STAT, CRA, CTA, other (excl meeting room and catering) |  |  | FX | 3500 | 0 | 0 | for initial meeting
9c | Investigator Meeting(s), subsequent meeting(s) |  |  | FX | 2000 | 0 | 0 | for subsequent meeting if relevant
9c | Investigator Meeting(s), results |  |  | FX | 3500 | 0 | 0
9d | Steering Committee meeting(s), includes time from PM, CI, STAT, EXT, PPI |  | 0 | FX | 3500 | 0 | 0 | up to 3/yr
9e | Study Team Meeting/Trial Management Group Meeting, included time from PM, CRA, CTA, CI |  | 0 | FX | 500 | 0 | 0 | based on 2h per meeting, 2-weekly
SUM | [5 empty] | 0 | 0
10 | IMP/Intervention Handling
10a | IMP or intervention Accountability | hours |  | Pharm | 60 | 0 | 0
10b | IMP/comparator/placebo/device (incl import license if appl) | units |  |  |  | 0 | 0
10c | Storage & distribution | hours |  | EXT |  | 0 | 0
10d | Packaging, blinding, labelling | hours |  | EXT |  | 0 | 0
10e | IMP destruction & recovery unused products | hours |  | EXT |  | 0 | 0
SUM | [5 empty] | 0 | 0
11 | External vendors/contractors/central review/other
11a | Study specific equipment | unit |  |  |  | 0 | 0
11b | External vendor | hours/unit |  |  |  | 0 | 0
11c | External Review | unit |  |  |  | 0 | 0
11d | Investigator meetings (meeting room and catering) |  | 0 | FX | 40 | 0 |  | forfait 40€ per participant - formula includes 2 participants per site, adjust if applicable
SUM | [5 empty] | 0 | 0
Overall Cost total | [5 empty] | 185600 | 185600
| Amount used to calculate FTE cost |  |  |  |  | 110600
| Amount used to calculate material cost |  |  |  |  | 75000
Note on H1: only include where relevant

## Site Costs BE
Trial |  | Number |  |  |  |  | DD/MM/YYYY
Per Patient Cost Belgium
Procedure | Total Budget | Screening | Treatment Phase |  |  | Study Treat discontinuation/ Early Termination Visit | FU Phase
|  |  | V1 | V2 | V…
General Procedures
Informed consent | 50 | 50
QoL questionnaires | 0
Procedures SubTotal | 50 | 50 | 0 | 0 | 0 | 0 | 0
Non Procedure
IMP or placebo dispensing if applicable | 0
Physician time | 100 | 16.6667 | 16.6667 | 16.6667 | 16.6667 | 16.6667 | 16.6667
Study Coordinator time (data entry) | 480 | 80 | 80 | 80 | 80 | 80 | 80
Non Procedures SubTotal (excl margin) | 580 | 96.6667 | 96.6667 | 96.6667 | 96.6667 | 96.6667 | 96.6667
Margin | 58 | 9.6667 | 9.6667 | 9.6667 | 9.6667 | 9.6667 | 9.6667
Non Procedures SubTotal (incl margin) | 638 | 106.3333 | 106.3333 | 106.3333 | 106.3333 | 106.3333 | 106.3333
Cost per completed patient | 688 | 156.3333 | 106.3333 | 106.3333 | 106.3333 | 106.3333 | 106.3333
VAT | 144.48
Total cost per patient | 832.48
General Site Costs
Number of sites BE | 0
start-up fee | 1000
Archiving (site-specific) | 250
Total general site costs/site | 1250
For all BE sites | 0
Costs for all BE patients | 0
TOTAL SITE COSTS BE | 0

## Site Costs NL
Trial |  | Number |  |  |  |  | DD/MM/YYYY
Per Patient Cost The Netherlands
Procedure | Total Budget | Screening | Treatment Phase |  |  | Study Treat discontinuation/ Early Termination Visit | FU Phase
|  |  | V1 | V2 | V…
General Procedures
Informed consent | 50 | 50
QoL questionnaires | 0
Procedures SubTotal | 50 | 50 | 0 | 0 | 0 | 0 | 0
Non Procedure
IMP or placebo dispensing if applicable | 0
Physician time | 100 | 16.6667 | 16.6667 | 16.6667 | 16.6667 | 16.6667 | 16.6667
Study Coordinator time (data entry) | 480 | 80 | 80 | 80 | 80 | 80 | 80
Non Procedures SubTotal (excl margin) | 580 | 96.6667 | 96.6667 | 96.6667 | 96.6667 | 96.6667 | 96.6667
Margin | 58 | 9.6667 | 9.6667 | 9.6667 | 9.6667 | 9.6667 | 9.6667
Non Procedures SubTotal (incl margin) | 638 | 106.3333 | 106.3333 | 106.3333 | 106.3333 | 106.3333 | 106.3333
Cost per completed patient | 688 | 156.3333 | 106.3333 | 106.3333 | 106.3333 | 106.3333 | 106.3333
VAT | 144.48
Total cost per patient | 832.48
General Site Costs
Number of sites NL | 0
start-up fee | 1000
Archiving (site-specific) | 250
Total general site costs/site | 1250
For all NL sites | 0
Costs for all NL patients | 0
TOTAL SITE COSTS NL | 0

## Overall costs
This tab is automatically calculated and serves for reference to ZonMW and KCE Trials - do not change!
| BE | NL | TOTAL TRIAL
Total Sponsor costs | 92800 | 92800
site BE | 0 | 0
site NL | 0 | 0
| 92800 | 92800 | 185600
expressed as FTE with a mean cost of 55€ per hour incl margin for the whole trial | 0.62841 | 0.62841 | 1.2568
expressed as FTE with a mean cost of 55€ per hour incl margin per year of trial duration | 0.052367 | 0.052367 | 0.10473
expressed as material cost (=non FTE) for the whole trial | 37500 | 37500 | 75000
expressed as material cost (=non FTE) per year of trial duration | 3125 | 3125 | 6250